## Slide 1: Race Organizer's Workshop 24 November 2016
Race Organizing Committee
Presented by Greta Brock

## Slide 2: Oh what a pity, I’m on a Committee
Meetings should be held at regular intervals for portfolio feedback BUT not everybody has to attend all meetings.
There are portfolios that play a role in the planning of the event -> these need to meet more often in the beginning.
There are portfolios that play a role on the day of the event -> these can join the meeting at a later stage when it becomes more relevant.
Nobody wants to waste time -> keep them short and relevant. A lot of discussions can take place in smaller sub-committees and/or via email.
For ease of contact create an email mailing list as well as a WhatsApp Group
The Secretary will take minutes as well as perform most of the administrative work, i.e. sending out invites to meetings, typing of letters and documents, printing, etc.
The Secretary is the central information hub and should be copied in all communication.

## Slide 3: Race Committee Members
Any Committee should have a
Chairman / Race Convenor / Race Director
Treasurer
Secretary
Plus
Any number of additional Committee members to fill the various portfolios
Portfolios can be combined
The more people there are to take on a specific portfolio the easier it gets

## Slide 4: Portfolios to fill
Liaison with City of Cape Town
Events package application
Matters arising from application
Liaison with Western Province Athletics
Entry Form / Race Flyer
  Design, approval, printing and distribution
Liaison with Technical officials
  before, during, after event
  Results
Liaison with WPA office
  Ordering / collection / return of entry cards, bank bags, safety pins, finishing sachets, temp licences
  Ordering / collection / return of equipment: results boards, cones, flags, clocks etc.

## Slide 5: Portfolios to fill -> required for Event Application
Venue
Hire, Lay-out, Liaison with property owner regarding lighting, access, toilets/change rooms, parking, neighbour hood notification
Route
Course layout, measurement, km boards, taping, cones, fencing, traffic plan, road closures
Refreshments
Location & person i/c of individual refreshment stations, ordering of water & Coke on route and at the finish, management on the day
Marshals
Parking, route, finish, lead vehicle/bicycle, sweeper vehicle
Safety & Security / Medical
Venue, parking, tog bags, registration
Safety Officer
Medical at venue / on route
Waste management
Route & Venue
Run Clean
Catering / Vendors
VIP’s, runners, spectators, officials

## Slide 6: Portfolios to fill cont.
Sourcing & Allocation of helpers
Inside the club, other clubs, organisations, companies
Admin/Registration
Pre-entries, database, race numbers, seeding
Registration venue lay-out, signage
Float & cash management
Marketing / Advertising / Media liaison
Social Media, Press, Radio
Before, during, after
VIP’s / Sponsors / Charities / Invited Athletes
Invitations, hosting, accommodation & transport
Tog bags
Start
Banner, starter’s gun, loudhailer/ sound system, announcer, bunting, start line, branding, start pens
Finish
Banner, chutes, announcer, branding, set-up for technical officials, timing, results boards
Handouts / Prize Giving
T-shirts, caps, goody bags
Medals, permanent numbers, certificates, lucky-draw
Prize Giving
Venue set-up, presenter, program
Transport
Collecting, distribution, return of equipment, water, helpers etc.

## Slide 7: Event Management Tool -> Project Status Report
Race Name: Fish Hoek 10 & 21.1 km challenge
Venue & Date Fish Hoek Athletics Club, 16 June 2017
Portfolio | Action Required | Person to action | Deadline | Status | Comments
Finance | Draw up budget | Treasurer | 10 Dec 2016 | Various quotes requested | Based on +/- 1500 runners
Route | Design of Route | Race Director Sue | 10 Dec 2016 | Provisional Route designed; to be discussed with WPA Road Running Comm. | Circular Route with 10 & 21 km option
Race Flyer | Design | Paul | 10 Dec 2016 | Flyer designed, sent to WPA for approval | A5, black & white, double sided, 10,000
 | Distribution | Paul Grant | 10 Dec 2017 | To be included in Marketing plan | 
Refreshments | Location | Carol | 10 Dec 2016 | Provisional plan discussed with Race Director & Sue | Subject to route approval by WPA & traffic
 | Ordering of Coke & Water | Carol | 01 June 2017 | Not started | 

## Slide 8: Available Resources
From the WPA Website: www.wpa.org.za
Governance
  Constitution & Policies
    2016 WPA Constitution
    Domestic Rules (Dec 2015)
  Athlete Insurance
  Anti Doping Documents
Officials – Resources
  Draft Referee Report
  Medical Incidents Report
  Payment Request – Technical Officials
Clubs – Club Resources
  ASA Rules & Technical Standards 2015
  IAAF Competition Rules 2016-2017
  Race Organizers Manual 2013
  WPA Fun Run Code of Conduct 2016
  City of Cape Town Events Application
Others (to be uploaded)
  Run Clean
  Budget Template