## Sheet1
New project funding request
Name of the project manager | Mr ABC
Department | Engineering
Funding request approved by (supervisor) | Ms XYZ
Date
Name of the project | Construction of a new clinic in ward 5
IDP reference number | HEA12/2021-22
Project guid
Funding guid
Function guid
Municipal standard classification guid
Costing guid
Region guid
Item guid
| Current year | MTREF Year 1 | MTREF Year 2 | MTREF Year 3
Budgeted amount required (capital budget)
Phase 1: Feasibility study (operating budget) | 100000
Phase 2: Detailed project planning |  | 450000
Phase 3: SCM processes |  | 10000
Phase 4: Project implementation |  |  | 1500000 | 1500000
Cost of consulting engineer |  |  | 150000 | 150000
Furniture and fittings to operationalise clinic |  |  |  | 500000
Landscaping and paving |  |  |  | 500000
Total project cost per year | 100000 | 460000 | 1650000 | 2650000
4860000
Total project cost over MTREF |  |  |  | 4860000
Project funding source | Operating revenue | Operating revenue | Borrowings | Borrowings
Projected cash flow per month
July |  | 50000 | 100000 | 200000
August |  | 100000 | 50000 | 200000
September |  | 100000 | 100000 | 200000
October |  | 100000 | 150000 | 200000
November |  | 100000 | 150000 | 200000
December |  |  |  | 100000
January |  |  | 100000 | 100000
February |  |  | 200000 | 200000
March |  |  | 200000 | 200000
April | 100000 |  | 200000 | 50000
May |  | 10000 | 200000 | 500000
June |  |  | 200000 | 500000
Total project cost per year | 100000 | 460000 | 1650000 | 2650000
| MTREF Year 1 | MTREF Year 2 | MTREF Year 3 | Outer years
ADDITIONAL operating cost required
Employee related costs |  |  |  | 50000
Provide details
Contracted services |  |  |  | 10000
Provide details
Operational costs |  |  |  | 10000
Provide details
Inventory |  |  |  | 5000
Provide details
Interest cost |  |  |  | 0
Provide details
Operating leases |  |  |  | 8000
Provide details
Depreciation and amortisation |  |  |  | 15000
Provide details
| 0 | 0 | 0 | 98000
98000
Total operating cost over MTREF |  |  |  | 98000
| MTREF Year 1 | MTREF Year 2 | MTREF Year 3 | Outer years
ADDITIONAL revenue generation potential
Service charges
Provide details
Operational revenue
Provide details
Rental from fixed assets
Provide details
Sale of goods and rendering of services |  |  |  | 5000
Provide details
| 0 | 0 | 0 | 5000
Total operating revenue over MTREF |  |  |  | 5000
Other information required
Consider issues such as:
Jobs to be created
Impact on local economic development
KPA addressed
KPI addressed
Desired impact
Desired outcome
Desired outputs
Activities required
Information related to capital prioritisation model of the municipality